## Daily_Status
Date | Platform | Task | Status | Total | Passed | Failed | Blocked | Not Executed | Owner | Remarks | Release | UAT Date | PROD Date
2026-09-17 | Web | Login regression smoke | In Progress | 40 | 28 | 3 | 2 | 7 | Sample Owner A | SAMPLE ROW 1 - Synthetic data | R2026.09.1 | 2026-09-20 | 2026-09-27
2026-09-17 | Android | Checkout critical path | At Risk | 30 | 18 | 6 | 3 | 3 | Sample Owner B | SAMPLE ROW 2 - Synthetic data | R2026.09.1 | 2026-09-20 | 2026-09-27
2026-09-17 | iOS | Notification end-to-end | On Track | 25 | 22 | 1 | 0 | 2 | Sample Owner C | SAMPLE ROW 3 - Synthetic data | R2026.09.1 | 2026-09-20 | 2026-09-27